The "Bid-Ready" Decision Matrix

Purpose: To provide an objective, non-emotional framework for assessing funding opportunities. This tool specifically filters out "Toxic Contracts" (those with high risk and low return) identified by local leaders.

Instructions:

- 1. The Lead Partner and Delivery Partners should complete this separately.

- 2. Compare scores. If there is a discrepancy (e.g., the Lead scores it a 'Go' but the Grassroots Partner scores it a 'No-Go'), resolve the risk before bidding.

| Criteria | Red Flag (Score 0) | Caution (Score 1) | Green Light (Score 2) | Your Score |
| --- | --- | --- | --- | --- |
| 1. Strategic Fit | Mission Drift. Chasing money to survive. No alignment with charitable objects. | Vague Alignment. Requires creating new services from scratch or stretching current delivery. | Direct Fit. Aligns perfectly with the current business plan and core expertise. |  |
| 2. Financial Reality | Subsidised. Contract value is fixed for 3+ years with no inflation link (Toxic). | Delivery Only. Covers direct costs but makes no contribution to Core Costs/Overheads. | Full Cost Recovery. Covers Delivery + Core + Management Fee + Inflation Link. |  |
| 3. Inflation Proofing | Flat Cash. Contract spans multiple years with 0% uplift clauses. | Discretionary. Review clause exists ("may be reviewed") but is not guaranteed. | Index-Linked. Annual uplift explicitly linked to CPI or National Living Wage. |  |
| 4. Mobilisation Gap | Immediate Start. Delivery expected on Day 1. No funded setup time. | Compressed. Short lead-in (2-4 weeks). Recruitment risk is high. | Funded Phase. A specific 1–3 month mobilisation phase is built into the budget/timeline. |  |
| 5. Payment Terms | 100% Arrears. Payment by Results or upon completion (High cashflow risk). | Mixed. A combination of upfront and arrears payments. | Upfront. Quarterly or annual payments in advance. |  |
| 6. Admin Ratio | Disproportionate. High reporting burden (e.g., 40+ page contract) for low value (<£5k). | Moderate. Standard reporting burden. | Light Touch. Admin is <10% of the total grant value. |  |
| 7. Partnership Trust | "Shotgun Wedding." Forced partnership for the bid with unknown entities. | New Partners. No history, but good reputation/references. | Established. Pre-existing, high-trust relationship. We know their work. |  |
| 8. Geographic Scope | Mismatch. Requires delivery outside our footprint (e.g., West Mercia) with no partners there. | Regional. Requires wide reach; we have potential partners but no formal agreement. | Local Fit. The delivery area matches our exact footprint (e.g., Telford & Wrekin only). |  |

- Decision Guide:

- • < 10 Points: NO-GO. The risk to reserves and reputation is too high. Do not bid.

- • 10 - 13 Points: PROCEED WITH CAUTION. Use the "Push-Back" Scripts (Tool 4) to negotiate on Red Flag areas.

- • 14+ Points: GO. A healthy, viable opportunity.